AGENDA

REGULAR MEETING

WATERFORD SCHOOL BUILDING COMMITTEE

WATERFORD, CONNECTICUT

PLEASE NOTE:  THERE WILL BE A TOUR OF WATERFORD HIGH SCHOOL STARTING AT 4:30 P.M.  PLEASE MEET IN THE LOBBY OUTSIDE OF THE MAIN OFFICE TO BEGIN THE TOUR.  THE MEETING WILL BEGIN AT 5:30 P.M. IN ROOM N1 AT WATERFORD HIGH SCHOOL.

DATE:		Tuesday, June 19, 2012

PLACE:	Room N1, Waterford High School

TIME:		5:30 p.m.

I. 	Establishment of Quorum and Call to Order

##### II.	Recognition of Visitors/Public Comment

##### III.	Correspondence/Informational Items

- FY2012 Capital Projects Contractual Commitments dated 5/16/12 from Rudie Beers, Director of Finance

##### IV.	Superintendent’s Report

##### V.	Old Business

  - Approval of Minutes:  May 10, 2012

##### VI.	New Business

- Renovate As New Status Update.

MOTION:  That the Waterford School Building Committee authorizes the School Building Committee Chair to sign appropriate documents for submittal and review to the Bureau of School Facilities for the Renovate As New Status for Waterford High School.

- Approval of ED-042, Project #152-0102 EA, Phase 2 of 3, Waterford High School, consisting of Furniture, Fixtures and Equipment (FF&E), and Instructional Technology (IT)

MOTION:  That the Waterford School Building Committee approve the ED-042, Project #152-0102EA, Phase 2 of 3, Waterford High School, consisting of Furniture, Fixtures & Equipment , and Instructional Technology and authorize the Committee Chair to sign same.

##### VII.	Consent Agenda

##### WATERFORD HIGH SCHOOL CHANGE ORDERS:

New Building Addition Items:

- Ducci/ITS proposal, in the amount of $36,226.30, for equipment to interconnect all the Town of Waterford Schools to the Central Station Receiver located in the Police Department Communications Center. The equipment will be installed by the Town of Waterford.  This will eliminate all Fire Alarm phone lines in all the schools.

- Advanced Performance Glass Proposal dated 6/1/12, in the amount of $5,241.13, for the revisions to CW-11 and E-21 in the connector bridge, due to the conflicts with the existing column, per RFI#509.  This price includes additional storefront and curtain wall lengths, additional Centria panels, additional brake metal, and an additional 42 SF of glazing.  APG cannot provide a credit for the deleted leaf of door C214 because it was a custom product that was ordered months ago, they did however deduct the labor to install the leaf when putting together this proposal, and will turn the door & door hardware over to the Owner.

- Advanced Performance Glass Proposal dated 6/1/12, in the amount of $1,093.32, to provide a storefront divider between doors H166A & H166B to match the one between H165A & H165B, per RFI#546.  This price includes 20 SF of additional glazing, the storefront stock lengths are being provided at no charge.

- Ducci Quote #74, to provide emergency power to all of the security card readers in the new building and renovation area, per RFI#347.  This work includes (5) dedicated circuits and 2390 LF of cable.  Circuits for the security card readers were not shown on the contract drawings.

- $19,705.00 to provide an M/C Cable System

- Ducci Quote #73, in the amount of $1,073.00, for the added costs to add power to the Aircuity & BMS panels in room H26, per RFI#466.  These panels were not shown on the power plans.

- HHS Proposal dated 5/23/12, in the amount of $4,431.11, for the piping of a 2nd coil for the DOAS Unit, per RFI#460.  The contract drawings and specifications do not reflect the need for (2) coils each for the chilled and hot water systems.  An additional detail was required.

- Secondino PCO#49, in the amount of $11,499.00, to change the WW3 and WW4 louvers from the originally specified units to custom sized Fypon units.  This price includes the (5) 72” diameter louvers and installation.  It also includes a credit of ($1,770.00) for the originally specified units.

- Conn Acoustics Change Request #41, in the amount of $306.13, to frame, sheetrock, and tape a new soffit in room F140 to hide a sprinkler pipe that would have been below the hung ceiling, per RFI#493.

- Conn Acoustics Change Request #42, in the amount of $3,812.39, for the installation of 550 additional 2 foot tees to accommodate the installation of the chill beams throughout the new building.  The chill beams are manufactured for a metric grid and this condition was unforeseen until installation began.

- Ducci Quote #59, in the amount of $7,870.00 (this price was reduced from the original amount of $9,151.00), for added power requirements for the DOAS Unit per the Manufacturer’s submittal. Per RFI#406, motor schedule shows (2) circuits but submittal shows (4) circuits requirements.

- Ducci PCO#68, in the revised amount of $23,176.00, to add (24) additional junction boxes, (4) each above the acoustical ceilings of six (6) science classrooms and associated electrical circuiting and breakers, per JCJ Proposal Request #46.  Ducci’s price does not include the cord reels and harwiring, the Town will use existing cord reels from the ‘J’ Building.  Ducci’s price to include cord reels is $42,406.00.

- Ducci PCO#75, in the amount of $583.00, to install an additional light in the exterior canopy at the 2nd floor entrance to Area H, RFI#572A regarding the changes to the lighting layout due to issues with the steel beams.

- RFI#577 to add double wide masonry openings on the east & west side of Room F214 and delete the door and the kiln.

- Capasso Proposal #37, in the amount of $7,977.00, to cut (2) new openings, install jamb blocks and bond beam blocks.

- Professional Painting Proposal dated 6/12/12, in the amount of $495.00, to touch up the walls.

- Waiting prices for: ACT removal and reinstallation, Electrical removal, all MEP for Kiln, louver to remain.

- Per RFI#576 Math Room F325 will become a multi-use math and science room.  Science casework will be added, including a demo station, cabinets and (2) sinks, and (2) ceiling mounted cord reel outlets, flooring was changed from carpet to sheet vinyl.

- Ducci PCO #82, in the amount of $4,938.00, to provide (2) ceiling junction boxes for cord reels along with power and data at teachers station, price excludes cord reels.

- Need pricing from HHS, Secondino, and Higgins

- Professional Painting proposal dated 9/8/11, in the amount of $833.00, for painting the added CMU wall, hollow-metal door, and frame in room H180, per JCJ Proposal Request #21.  Credit proposals for deleted work included:

- PR#23: Delete paint for a deleted wall in G186, credit of ($51.00).

- PR#25: Delete painted walls and painted door frame, credit of ($357.00).

- PR#36: Delete painted wall in G344, credit of ($138.00).

- RFI#364C: Delete painted walls of G187, credit of ($102.00).

- Total added cost for this change is $185.00.

- RFI#587, delete ceiling in rooms F308 & G362 for attic access ladder use, paint exposed structure P-9 (white), replace lights with pendant light fixtures (save the ones in the contract drawings for use in the J Building), hard pipe the supply and returns, and rake all CMU joins as a finished product.

- Conn Acoustics Change Request #45, in the credited amount of ($1,234.80), to delete the ACP-1 acoustical ceiling from rooms F308 & H362.

- HHS proposal dated 6/8/12, in the amount of $1,368.80, to re-feed FCU H364 from the CHW S&R as opposed to the DTW S&R as shown in the contract drawings, per RFI#589.

- Ducci PCO #80, in the amount of $2,733.00, to furnish and install (1) type ‘Y’ light fixture on the Stair #2 landing between the 1st and 2nd Floors, per RFI#444.  The quote from Rexel for the type ‘Y’ fixture is $1,470.00.

- Ducci PCO #81, in the amount of $2,874.00, to provide an alternate type ‘R’ fixture for use at the cafeteria storefront and the additional labor to mount these larger units, which involve additional bolting into the masonry, per RFI#578.

- RFI#529 regarding the clarification of the location of the CUH throughout 1st Floor Area H.  Electrical and Mechanical drawings were not coordinated.

- Ducci PCO #78, in the amount of $1,490.00, to provide power to CUH-1 & CUH-2.  These CUH’s were not shown on the power plans.  Ducci to provide an additional 180 LF of wire and fittings.

- Ducci PCO#77, in the amount of $1,428.00, to provide power to fan REF-2, per RFI#523 regarding the missing circuiting information for Fan REF-2 in Area H.  Ducci to provide an additional 280 LF of wire and fittings.

- HHS Proposal dated 5/23/12, in the amount of $1,993.35, for the relocation of the transfer duct in the Head End Room due to the resizing of room G154, per RFI#222B.

- Ducci PCO #79, in the amount of $9,489.00, to provide CAT-6 to the locations shown on SKCOM 1.09R, from JCJ PR #14, this is for approximately 5,400 LF of CAT-6.

- JCJ PR 14: Communication Changes per Town of Waterford Technology Department. Ducci Electrical Quote #28, in the amount of $297,538.00, this price was revised to $208,890.00, a second revision was sent revising the price to $159,420.00, the third revision was in the amount of $141,488.00.  The current revised amount is $144,323.00; this revision was sent to include the 4-post racks. Additional Excavation is excluded.

Breakdown:

- Delete Multimode J Bldg to and Townhall

- Add 24SM & 24MM OM3 fiber between J building and new Bldg

- Add 24SM BEF H186 to MDF G154

- Delete Addendum #4 Paragraph #3

- Add 25 Pair Copper from J Bldg to Filedhouse Bldg B148

- Reduce 100 Pair to 25 Pair from MDF to each IDF.

- Add Patch Panels and (48) Cat 6 cables from MDF to V-Brick rack in media ctr.

- Increase WAP Cabling from (1) cable to (2) cables in (15) select high density room.

- Add WAP cabling in Auditorium & Filehouse.

- Add OSP cabling for WAP's

- Revise Classroom Layout.

- Add WAP cabling in cafeteria.

- Add data drops for Mobile printers.

- Revise Media center cabling layout

- Revise cabeling layout in (5) rooms.

- Add intra building Coaxial cable to aux gym, auditorium, fieldhouse, Media ctr, TV Studio, and fiber optic cabling to football and baseball field press boxes per SKCOM1.02R, SKCOM 1.04 and SKCOM 1.05

Field Items:

- Secondino/Deedy Quote dated 4/3/12, for T&M work, in the amount of $3,569.50, for the installation of a 1 ½” waterline to the football field concession stand and an extension to the hydrant.

- RFI#548 (SKA-100) to add an additional coiling overhead door in the concession stand and modify the millwork, per owner request.

- Secondino PCO#50, in the amount of $6,795.53, for the added overhead coiling door and the changes to the millwork.

- Capasso Proposal #36, in the amount of $5,923.00, to cut the opening for the overhead door, install new jamb block and bond beam block.

- The total added cost of the change is $12,718.53.

- Ducci PCO#69, in the amount of $81,091.00, to add AV sound systems for  the football field and baseball field, per JCJ Proposal Request #44, for the following:

Football Field & Track

- 5 Community Speakers and the Pole Mounts

- 3 Amplifiers

- 1 Signal Processor with Volume Control & Custom Plate

- 1 CD Play Deck

- 1 Wireless Mic Antenna

- 2 Wireless Mics (1-Handheld, 1-Lapel)

- 1 Announcement Mic

- 1 Equipment Rack

Baseball Field

- 2 Community Speakers and the Pole Mounts

- 2 Amplifiers

- 1 Signal Processor with Volume Control & Custom Plate

- 1 CD Play Deck

- 1 Wireless Mic Antenna

- 2 Wireless Mics (1-Handheld, 1-Lapel)

- 1 Announcement Mic

- 1 Equipment Rack

- New Score Boards for the Football & Baseball Field, per JCJ Proposal Requests #32 & 33.  Had meeting with Jaypro on 4/25/2012.  Secondino pricing mounting, engineering, concrete sonotubes to follow.

Scoreboard :

- Electro-Mech Football Field Scoreboard (26’x10’ Model #3695) with “HOME OF THE LANCERS” Logo, Wireless Receiver, Wireless Controller, & Carrying Case for Controller: $21,175.00 (Jaypro).

- Electro-Mech Baseball Field Scoreboard (20’x6’ Model #LX1737) with “HOME OF THE LANCERS” Logo, Wireless Receiver, Wireless Controller, & Carrying Case for Controller: $17,875.00 (Jaypro).

Site Items

- Additional work to prepare the site for general public occupancy, to be performed by Secondino/Deedy/Eagle Fence:

- Mowing, site prep and grading, clean-up, in the amount of $7,480.00

- 8’ Temporary fencing rental around sediment basin, in the amount of $5,280.00 up to 9/1/2012.

- Fucci CO#45, in the amount of $41,245.34, to furnish and install roof leader drain connections into the storm drainage system, per RFI#269 (CSK#14).  This proposal includes:

- 180 tons of bedding material

- 770 LF of SDR-35 Pipe

- Fittings for (12) downspout tie-in locations

- Contractor reserves right for additional time added to the contract as a result of the additional work.

- Fucci CO#48, in the amount of $11,848.55, for the relocation of the previously installed PIV and water gate due to a conflict with the location of the site pavers, per RFI#449A.  The layout of the curb line on the utility plans did not match the curb line on finish plan.  Fucci revised their price to provide a credit in the amount of ($2,524.00) for the elimination of the 4” Fire Protection Stand Pipe piping, per RFI#494, bringing the total for this change to $9,324.55. Contractor reserves right for additional time added to the contract as a result of the additional work.

Auditorium & Stage/Lobby Items

- Professional Painting quoted dated 5/25/2012, in the credited amount of ($5,593.00), to replaces the ScuffMaster Paint with an epoxy paint, at the owner’s request for maintenance purposes, per RFI #555.  This covers the following areas:

- C101 & 102 Lobby – All columns, except those along south wall

- C102/210 Lobby – CMU walls of elevator enclosure

- C114 Auditorium – Handrails

- C128 Stair 7 – stringers and handrails

- C129 Stair 8 – stringers

- C132 Stair 13 – stringers and handrails

- C211 Stair 12 - stringers

- D101 Lobby – handrails

- Stair 2 (F Building) – handrails, railings, & stringers

- HHS/WACO proposal, in the amount of $75,524, for the shipping, erecting, dismantling, and 2 months of rental of scaffolding for the construction of the Auditorium Catwalk.  An additional rental charge of $7,885.70 + 10% OH&P will be charged for each additional 28 day period.  Two other prices were obtained:

- New England Scaffolding, Inc.: $105,700.00 for the same services.

- Advanced Scaffold Services of NE LLC: $110,000.00 for the same services.

- HHS Proposal dated 5/31/12, in the amount of $2,432.23, to provide floor drains and trap primers in toilet rooms C104 & C105, per RFI#564.  Drains were not shown on the contract drawings.

- Secondino/Deedy proposal dated 5/11/12, in the amount of $9,800.00, to expose steel beams in seven (7) different locations in the Auditorium Stage Area, this demo was not shown on the plans.

- Advanced Performance Glass proposal dated 5/15/12, in the amount of $35,384.37, to furnish and install a new CW-1 to replace the existing CW-1, per JCJ Proposal Request #47.  This works out to approximately 350 SF of new glazing at $101/SF.  Doors C102C and C102D and their hardware sets are not included in this proposal, as they were carried in the base bid.

- Per JCJ Proposal Request#48 scope was deleted from the work in Room C120 (Shane’s stage office).

- Conn Acoustics Change Request #43, in the credited amount of ($1,289.94), for the deleted shaftwall ceiling in Room C120.

- Professional Painting Proposal dated 6/5/12, in the credited amount of ($137).  This price includes a $54 add for the additional painting and a credit of ($192) for the deleted work.

- M. Frank Higgins Proposal dated 5/7/12, in the amount of $11,192.50, to repair and refinish the auditorium stage floor (including painting the matt black finish).

- RFI#575, the ceilings in rooms C106-C110 are called out as existing to remain, these were changed to ACP-3 in C107 & C110, ACP-1 in C108 & C109, and existing ceiling to remain in C106.  Type ‘C’ light fixtures were also added.  Sketches to be provided in Phase 3 Documents.

- Conn Acoustics Change Request #44, in the amount of $5,268.87, for 230 SF of ACP-3 and 330 SF of ACP-5.  This price was revised to $3,722.49, to use ACP-1 in lieu of ACP-5.

- Ducci PCO #76, in the amount of $3,291.00, to furnish and install (6) type ‘C’ light fixtures in rooms C106, C108, & C109.

- RFI#549 regarding the change from concrete construction in the Auditorium Lobby to structural steel.  The purpose of this change is to speed up the construction in this area.

- Shepard Change Order Request #M5, in the amount of $14,881.00, to add Stair #7, as a structural Steel stair.

- Shepard Change Order Request #7, in the amount of $22,732.55, for fabrication and erection of new steel framing and structural supports in SKA-S08 thru SKA-S13.

- Conn Acoustics Change Request #40, in the amount of $2,402.86, for the changes to the Area B Canopy to allow it to be constructed with a hard ceiling as desired by the architect, per RFI#519

Pool & Fieldhouse items

- HHS quote dated 5/23/12 for T&M work on 5/4/12, in the amount of $473.79, for the installation of safety wires on the Fieldhouse diffusers.

- Secondino/Deedy Proposal dated 5/11/12, in the amount of $6,800.00, to remove and dispose of the plaster wire mesh, metal framing, and insulation from the Area A Canopy at the Pool Entrance.  This work was not shown on the demo plan.

##### VIII.	WATERFORD HIGH SCHOOL

##### Architect’s Report Waterford High School: JCJ Architecture

##### Construction Manager’s Report Waterford High School: O&G

##### Pending Items:

- Possible elimination of the retention pond on west side of property - ongoing

- Practice field layout - ongoing

- Musco lighting - ongoing

- Football field concession stand - pending

- Scoreboards – reviewing logos

- Auditorium catwalk- sketches forthcoming

- WHS sign(s) on building - ongoing

- Diving board and pool scoreboard – investigating

- Auditorium Stage Floor water damage – ongoing

- Pool Tile Repair – scheduled

- Tennis Court Lighting

- Remove White Pines (Rope Ferry Road) to add visibility

##### IX.	Bill List—See Attached

##### X.	Adjournment

##### IX.	Bill List June 19, 2012

| Project #152- | School | Stage | Vendor | Description | Invoice# | Amount |
| --- | --- | --- | --- | --- | --- | --- |
| n/a | WHS | n/a | Allied Restoration | Roofing | 00009 | $63,400.63 |
| n/a | WHS | n/a | O&G | CM services | 00017 | $103,096.00 |
| n/a | WHS | n/a | Advanced Performance | Entrances & Storefronts | 00008 | $160,277.24 |
| n/a | WHS | n/a | Conn Acoustics, Inc. | Drywall & Acoustical | 00012 | $165,882.73 |
| n/a | WHS | n/a | HHS Mechanical | Fire Protection, Plumbing | 00015 | $401,529.66 |
| n/a | WHS | n/a | Shepard Steel & Co. | Structural metal framing | 00014 | $31,610.30 |
| n/a | WHS | n/a | Ducci Electrical | Electrical | 00013 | $506,131.27 |
| n/a | WHS | n/a | Joe Capasso Mason | Masonry | 00011 | $293,030.33 |
| n/a | WHS | n/a | CJ Fucci | Sitework | 00014 | $265,811.98 |
| n/a | WHS | n/a | Professional Painting | Painting | 00009 | $40,025.40 |
| n/a | WHS | n/a | A. Secondino | General Trades | 00010 | $55,292.47 |
| n/a | WHS | n/a | M. Frank Higgins | Flooring | 00008 | $33,681.30 |
| n/a | WHS | n/a | Manafort Brothers | Concrete | 00009 | $28,267.03 |
| n/a | WHS | n/a | A. Secondino | Casework | 00003 | $155,534.60 |
| n/a | WHS | n/a | Joseph Theroux | Professional Services | 49-12 | $300.00 |
| n/a | WHS | n/a | Pak-It of SECT | Packing materials | 000101 | $28.98 |
| n/a | WHS | n/a | VanZelm | Professional Services | 0037292 | $3,371.64 |
| n/a | WHS | n/a | VanZelm | Professional Services | 0037192 | $3,371.64 |
| n/a | WHS | n/a | William B. Meyer, Inc. | Moving services | COM-540-2/1 | $4,483.00 |
| n/a | WHS | n/a | CLA Engineers | Professional Services | #2 | $3,385.00 |
| n/a | WHS | n/a | CL&P | Utilities | 51818835019 | $488.97 |
| n/a | WHS | n/a | CL&P | Utilities | 51818835019 | $436.40 |
| n/a | WHS | n/a | JCJ | Professional services | 0000044 | $35,365.00 |
| n/a | WHS | n/a | Eagle Leasing | Storage | R1423105 | $75.00 |
| n/a | WHS | n/a | Eagle Leasing | Storage | R1427652 | $140.00 |
| n/a | WHS | n/a | Eagle Leasing | Storage | R1426819 | $350.00 |
| n/a | WHS | n/a | Eagle Leasing | Storage | R1431690 | $70.00 |
| n/a | WHS | n/a | Eagle Leasing | Storage | R1430806 | $75.00 |
| n/a | WHS | n/a | Eagle Leasing | Storage | R1433026 | $375.00 |
| n/a | WHS | n/a | VHB | Professional Services | 0148194 | $6,488.50 |
| n/a | WHS | n/a | Cynthia Kaplan | Professional svc | 052012.113 | $1,160.00 |
| n/a | WHS | n/a | CorBuilt LLC | Utilities marking | 825129 | $1,680.00 |
| n/a | WHS | n/a | Mystic Air | Professional Services | 31091 | $275.00 |
| n/a | WHS | n/a | Ti Sales | Water meters | INV0012793 | $1,374.68 |
| n/a | WHS | n/a | Waterford Bd of Ed | Cust/maint | June 12, 2012 | $599.70 |
| n/a | WHS | n/a | Waterford Bd of Ed | Cust/maint | May 8, 2012 | $1,052.29 |
| n/a | WHS | n/a | A Royal Flush | Portable toilets | 420833 | $715.00 |
| n/a | WHS | n/a | A Royal Flush | Portable toilets | 421179 | $2,104.75 |
| n/a | WHS | n/a | A Royal Flush | Portable toilets | 421974 | $249.00 |
| n/a | WHS | n/a | A Royal Flush | Portable toilets | 423968 | $2,002.00 |
| n/a | WHS | n/a | A Royal Flush | Portable toilets | 423170 | $715.00 |
| n/a | WHS | n/a | Special Testing | Testing | 28286 | $5,927.00 |
| n/a | WHS | n/a | Special Testing | Testing | 26301 | $5003.50 |